## Sheet1
Quarterly & Yearly Plan
Quarter | Goals | Milestones
Q1 | - Research ML Models | - Milestones ranked and top choice identified
| - Research and select API framework | - Framework is selected
| - Research house pricing | - Plan developed for the workings of the house pricing prediction program
Q2 | - Develop the API | - API working locally with example routes
| - Develop the model prediction program | - Program successfully creates predictions
Q3 | - Combine the model prediction program and API | - Model predictions can be made using a POST request
| - API is tested and optimized | - Passes all unit tests in Github Actions
Q4 | - API is deployed to Azure using Github actions and Azure pipelines | - Production API is published and accessible for all users
| - Metrics and alerts configured | - Real time email notifications are set up
Yearly | - Develop and deploy a ML house price prediction API | - Full functional web app deployed to Azure
Weekly Deliverables
Week | Task
1 | Create codebase for api
2 | Create ML prediction code
3 | Create fully functional api with ML predictions
4 | Write unit tests and make sure they're passing
5 | Set up Azure environment
6 | Deploy web app to Azure
7 | Set up alerts and metrics
Task Estimation
Task | Difficulty (1-5)
Create codebase for api | 3
Create ML prediction code | 4
Create fully functional api with ML predictions | 4
Write unit tests and make sure they're passing | 2
Set up Azure environment | 3
Deploy web app to Azure | 3
Set up alerts and metrics | 2